## Roadmap Overview
LIGHTPATH PLATFORM ROADMAP
Organized by dependency, trust, and platform maturity — not time
Stage | Name | Purpose | Prerequisites | Workstreams | Gate Items | Felt Improvement
Stage 1 | Trust Baseline | Make the platform safe enough to trust, stable enough to build on, and instrumented enough to measure change. | None — this is the starting point. | 6 | 17 | The user sees working legal links during sign-up. Keyboard users can navigate core flows. Crisis mode actually protects. Error messages are announced to screen readers. The team can see where users drop off.
Stage 2 | Shared Brain | Create the platform's shared intelligence layer so every surface reads from the same mind and no question is asked twice. | Stage 1 gate passed. RLS is sound. Analytics is live. | 4 | 7 | The platform stops asking the same question twice. Today's recommendations become more specific. Users who report sleep disruption in T3 see rest-focused suggestions in Today.
Stage 3 | Operational Clarity | Make Care Plan visibly smarter without making it heavier. Fastest path to users feeling the platform's intelligence. | Stage 2 gate passed. Shared state available. Signal routing works. | 3 | 7 | Users open Care Plan and immediately know which tasks they can do today, which are blocked, and what's missing. Vault feels connected to tasks. Crisis/rest mode users see gentle containment.
Stage 4 | Visible Intelligence | Make the user feel the platform's intelligence. Today becomes an orchestrator. LightKeeper becomes warm and specific. | Stage 3 gate passed. Task readiness exists. Vault linkage works. | 4 | 8 | Today feels like it knows the user. LightKeeper's first message makes the user feel seen. Recommendations explain themselves. The companion references platform activity.
Stage 5 | Continuity + Support Formulation | Turn LightKeeper into a real continuity layer with structured memory and clinical-grade support formulation. | Stage 4 gate passed. Full context injection works. User research available. | 7 | 11 | LightKeeper remembers. Support formulation makes the user feel understood. Companion tone matches preferences. Professional help suggested with dignity.
Stage 6 | Deep Clinical Engine + Cross-Surface Wiring | Make Inner Light more routed and scenario-aware. Wire remaining cross-surface connections. One coordinated system. | Stage 5 gate passed. Support formulation exists. Memory works. Shared brain mature. | 5 | 10 | Platform feels like one coordinated system. Inner Light knows what LightKeeper knows. Guides relevant to active tasks. Today remembers yesterday. Every question explains why.
Stage 7 | Ecosystem Coordination | Extend intelligence beyond the individual user to their support network and professional care providers. | Stage 6 gate passed. Cross-surface wiring complete. Support formulation mature. | 4 | 5 | Platform starts to feel like coordinated care. Supporters know how to help. Professional care available when needed. Important dates acknowledged.
Stage 8 | Learning + Scale | Make the platform measurably improve over time. Build the systems that learn from real use. | Stage 7 gate passed (or Stage 6 for some items). | 6 | 6 | Platform gets smarter over time. Recommendations improve. Tasks have more automation. Product learns from real use.
TOTAL |  |  |  | 39 | 71

## Workstreams
ALL WORKSTREAMS — Detailed Scope
ID | Stage | Workstream | Priority | Owner | Scope | Dependencies | Notes | Status
1.1 | Stage 1 | RLS Security Redesign | CRITICAL | Sara | Drop debug_list_policies(). Restore auth.uid() to get_user_journeys(). Replace JWT-claim vault_supporters policies with denormalized column. Reduce 8 SECURITY DEFINER functions to 2. Write pgTAP cross-user isolation tests. Document final permission model. External Supabase RLS review. | Security audit findings | Hard gate — blocks all new DB tables | Not Started
1.2 | Stage 1 | Crisis Safety Enforcement | CRITICAL | Sara | Complete adaptive phase limits in TasksApple (crisis=0, rest=1, grounding=2). Pass support_mode + safety_flags to companion AI edge function. Update buildDynamicSystemPrompt(). Add crisis_events table + logging. Add persistent 988/741741 footer in crisis mode. Verify all surfaces respect crisis suppression. | useSupportMode hook exists | Blocks companion AI improvements | Not Started
1.3 | Stage 1 | Critical Accessibility | CRITICAL | Sara | AriaLiveRegion component for all error/success. Vault PIN entry a11y (aria-labels, Tab nav, live region). Keyboard handlers on all div[role=button]. Form input aria-labels. Darken textFaint to pass WCAG AA. Skip navigation link. | None | WCAG AA minimum for production | Not Started
1.4 | Stage 1 | Trust Hygiene Sweep | HIGH | Sara | Fix broken ToS/Privacy links (currently href='#'). Complete getProgressEncouragement() stub. Wire TaskCompletionCelebration to TaskDetailPage. Connect useReprofilingPrompt to UI. | None | User-facing trust signals | Not Started
1.5 | Stage 1 | Analytics Event Schema + Baseline | HIGH | Sara | Integrate PostHog. Instrument onboarding funnel (10 events). Instrument feature engagement (15+ events). Instrument crisis events. Compute DAU/WAU/MAU retention baseline. | None | Ongoing — measurement from day one | Not Started
1.6 | Stage 1 | Dose Enforcement | HIGH | Sara | Move dose tracking from localStorage to Supabase (intervention_doses table). Enforce dose limits server-side. Respect limits across devices. | 1.1 (RLS sound for new tables) | Therapeutic safety | Not Started
2.1 | Stage 2 | Canonical UserState | CRITICAL | Sara | Define CanonicalUserState TypeScript interface (identity, profile, emotional, engagement, safety, derived fields). Implement useCanonicalUserState() hook composing existing hooks. Migrate all surfaces to read from it: Today, Inner Light, LightKeeper, Guides, Marketplace. | 1.1 complete | Foundation for all intelligence | Not Started
2.2 | Stage 2 | Profile Signal Registry + Dedup | HIGH | Sara | Map all 68 questions to signal names. Identify canonical source per signal. Implement hasSignal()/getSignal(). Deduplicate T2 vs T1 (5 overlaps), T3 vs T1 (3 overlaps). Remove or deprecate ComprehensiveIntake component. | 2.1 (shared state) | Stops asking same question twice | Not Started
2.3 | Stage 2 | Answer Routing | HIGH | Sara | Define SignalConsumer registry — for each signal, declare what changes when answered. Implement signalUpdated() event propagation. Wire 15+ missing consumer connections (loss_circumstance → LightKeeper tone, daily_checkin → Inner Light suggestion, etc.). | 2.1, 2.2 | Answers flow to every surface | Not Started
2.4 | Stage 2 | Typed ClinicalRoute + Stronger SupportMode | CRITICAL | Sara | Add dominant_suffering_type, loneliness_type, provider_need_likelihood to SupportMode. Define ClinicalRoute type (peer/companion/professional/crisis) with derivation function. Define TodayPayload contract. Ensure all surfaces consume SupportMode. | 2.1 | Clinical intelligence layer | Not Started
3.1 | Stage 3 | TaskReadiness | CRITICAL | Sara | Define TaskReadiness states (ready/blocked/waiting/deferred) with reason, missing_thing, unblock_action, vault_link. Compute from task-dependencies (41 chains) + task-operations-specs (50 outcomes) + T2 eligibility + vault document inventory. Surface in UI: readiness badges, 'What's needed' section. Complete adaptive task count with mode-appropriate language. | 2.1, 2.3 (signals flow) | Users know what they can do NOW | Not Started
3.2 | Stage 3 | Vault ↔ Care Plan Deep Link | HIGH | Sara | Add 'Open in Vault' from task detail when vault_requirements exist. Show per-requirement document status on task detail. Warm Vault empty states with task context. When document uploaded → update task readiness → surface in Today. | 3.1 (readiness states) | Vault feels connected, not empty | Not Started
3.3 | Stage 3 | Authority Visibility | MEDIUM | Sara | Show authority context on tasks requiring it. When user authority doesn't match → explain and offer delegation. Connect to delegation logic. | 3.1 | Users understand task ownership | Not Started
4.1 | Stage 4 | Today Intelligence Upgrade | CRITICAL | Sara | Upgrade moment interpretation with dominant_suffering, practical_burden, support_environment. Upgrade section scoring (tasks weighted by readiness, LightKeeper by loneliness, Inner Light by suffering type, Guides by active tasks, Find Care by provider need). Add 'Why this recommendation' explanations. | 3.1 (readiness), 2.4 (clinical route) | Today feels like it knows the user | Not Started
4.2 | Stage 4 | LightKeeper First-Use Redesign | HIGH | Sara | Replace T4 personality quiz barrier. Redesign first message using existing T1 signals (deceased_name, loss_circumstance, help_focus, grief_phase). Eliminate 'No messages yet' cold state. Companion speaks first based on what it knows. | 2.1 (shared state) | First message makes user feel seen | Not Started
4.3 | Stage 4 | LightKeeper Full Context Injection | HIGH | Sara | Expand companion AI payload: LightKeeperSupportProfile, active tasks + readiness, Inner Light outcomes, daily check-in moods, guide completions, T3 signals, boundaries. Update buildDynamicSystemPrompt() with preferred tone, boundaries as hard constraints, pacing guidance. | 1.2 (safety context), 2.1 (shared state) | Companion references platform activity | Not Started
4.4 | Stage 4 | First User Research Sessions | HIGH | Sara | 5 grieving participants, 45-min sessions. Test 6 hypotheses: profiling disconnected from value, dashboard sparse, task phases confuse, LightKeeper cold, Vault premature, no 'start here'. Licensed counselor on standby. Capture time-to-first-action, comfort ratings, trust scores, return intent. | None (can start early) | Validates or refutes assumptions | Not Started
5.1 | Stage 5 | LightKeeperSupportProfile Schema | CRITICAL | Sara | Define full TypeScript interface (loss_context, dominant_suffering, loneliness_type, support_need, connection_preference, depth_readiness, boundaries, safety_status, match/tone/frequency preferences, nuance signals, outcome_history, derived fields). Create Supabase table with RLS. Create useLightKeeperProfile() hook integrated with CanonicalUserState. | 1.1 (RLS), 2.1 (shared state) | Storage for support intelligence | Not Started
5.2 | Stage 5 | Support Formulation Phase 1 | CRITICAL | Sara | 10 questions, one per screen, <5 min. Signal dedup: reads T1 for relationship, loss_date, circumstance, faith. 7 net-new questions: support_need, dominant_suffering, loneliness_type, connection_preference, depth_readiness, boundaries, safety. Safety routing: crisis → stop matching, route to 988. Post-completion 'Your support fit' summary. Signals feed SupportMode, Today, Inner Light. | 5.1, 2.2 (dedup) | User feels understood, not surveyed | Not Started
5.3 | Stage 5 | Support Formulation Phases 2-3 | HIGH | Sara | Phase 2 (8 Qs): relational fit — match preference, tone, frequency, format, anti-patterns. Appears after first LightKeeper interaction, not front-loaded. Phase 3 (7 Qs): nuance — faith, culture, support environment, practical burden, grief narrative, overwhelm factors. Optional, revisitable. Signals feed companion system prompt and Today scoring. | 5.2 | Progressive depth without burden | Not Started
5.4 | Stage 5 | Phase 4 Learning Loop | HIGH | Sara | 5 post-interaction questions: felt outcome, fit assessment, next preference, feedback, consent to adjust. Escalation trigger: 'worse' twice → increase provider_need_likelihood → surface professional help. Feeds companion adjustment, Inner Light refinement, Today scoring. | 5.2 | Platform learns what helps | Not Started
5.5 | Stage 5 | LightKeeper Memory Schema | CRITICAL | Sara | Design memory schema: shared_facts (with source, importance), emotional_patterns (with confidence, evidence), preferences (tone, topics, depth, what helped/didn't), continuity (last summary, open threads, promises, milestones). Supabase table with RLS. Memory updated after each conversation by companion AI summarization. Inject into companion context. | 5.1 (schema), 4.3 (context injection) | LightKeeper remembers | Not Started
5.6 | Stage 5 | Matching Engine | MEDIUM | Sara | Three-layer matching: hard filters (safety, age, language, consent, boundaries), strong weights (support need 40%, depth 20%, tone 15%, boundaries 15%, readiness 10%), contextual weights (relationship 30%, time-since-loss 25%, life stage 20%, culture 15%, format 10%). Output: CompanionBehaviorProfile for AI tuning. Match explanation for transparency. | 5.2 (Phase 1 data) | Support feels personalized | Not Started
5.7 | Stage 5 | Escalation + Provider Routing | HIGH | Sara | Define triggers: safety Q10, outcome 'worse' x2, grief_wave >0.8 sustained, explicit request, trauma+traumatic circumstance. Warm non-pushy response. Surface Find Care with relevant categories. Frame as 'specialized attention' not failure. | 5.2, 2.4 (clinical route) | Professional help when needed, framed with dignity | Not Started
6.1 | Stage 6 | Inner Light ↔ Support Formulation | HIGH | Sara | Feed emotional_depth_readiness to tool selection (low→lighter, high→deeper). Feed dominant_suffering to intervention family (trauma→grounding, yearning→bonds, numbness→activation, guilt→self-compassion, practical→redirect to Care Plan). Feed boundaries as hard constraints. Feed outcomes back to support profile. LightKeeper references helpful tools. | 5.2 (formulation), Inner Light tools exist | Inner Light scenario-aware | Not Started
6.2 | Stage 6 | Guide ↔ Care Plan Connection | MEDIUM | Sara | Feed active_task_categories to useGuideRecommendations. Probate tasks → probate guides. Task completion → suggest related guide. Task detail → related guides. Guide detail → related tasks. Fix guide search empty state. | 3.1 (readiness), 2.1 (shared state) | Guides relevant to active work | Not Started
6.3 | Stage 6 | Marketplace ↔ Clinical Triage | MEDIUM | Sara | Feed provider_need_likelihood to marketplace. clinical_route='professional' → elevate Find Care. Phase 4 worsening → increase referral prominence. Add 'When to seek professional help' guidance card. Fix marketplace empty results. | 2.4 (clinical route), 5.4 (learning loop) | Professional care contextually surfaced | Not Started
6.4 | Stage 6 | Today Return Narrative | MEDIUM | Sara | Track session boundaries. Return visit → continuity sentence ('Since last visit, you completed X'). Mood change acknowledgment. Hard date approaching → gentle alert. 1 sentence of continuity, not activity log. | 1.5 (analytics), 2.1 (shared state) | Today remembers yesterday | Not Started
6.5 | Stage 6 | Question Architecture Polish | MEDIUM | Sara | T1: soft rationale, progress indicator, post-profiling summary, move Q8/Q9 out of essential. T2: group by context, completion nudge, propagate to Today scoring. T3: body/sleep → rest-mode, processing → LightKeeper, recurring thought/comfort → memory. QuestionRationale component for all flows. | 2.2 (signal registry) | Every question explains why | Not Started
7.1 | Stage 7 | Supporter Intelligence | HIGH | Sara | Supporter prompts when support_environment='Almost no one'. Scoped task delegation with authority context. Supporter dashboard showing needed help. Contextual 'Ask for help' buttons on delegatable tasks. | Stage 6 gate | Supporters reduce burden | Not Started
7.2 | Stage 7 | Provider-Aware Routing | HIGH | Sara | clinical_route='professional' → prominent Find Care. Provider recommendations by specialization, location, insurance, loss type. Warm handoff: pre-generated summary for provider with user consent. | 6.3 (marketplace triage) | Professional care well-matched | Not Started
7.3 | Stage 7 | Hard-Date Intelligence | MEDIUM | Sara | Track significant dates (anniversary, birthday, holidays). Pre-date: gentle warning. On-date: adjust support mode, surface grounding tools, LightKeeper acknowledgment. Post-date: gentle check-in. | 2.1 (shared state), 5.5 (memory) | Important dates acknowledged | Not Started
7.4 | Stage 7 | Document Readiness Coordination | MEDIUM | Sara | Cross-reference Vault documents with all task requirements. Dashboard-level summary: 'X tasks waiting for documents.' Supporter coordination for document gathering. Expiration/renewal tracking. | 3.2 (vault linkage) | Document readiness visible | Not Started
8.1 | Stage 8 | Route Effectiveness Scoring | HIGH | Sara | Track acceptance/dismissal for all recommendations. Track outcomes if accepted. Compute effectiveness score per type per user state. Use data to improve future recommendations. | 1.5 (analytics) | Recommendations improve over time | Not Started
8.2 | Stage 8 | What-Helped / What-Overwhelmed Memory | HIGH | Sara | Aggregate Phase 4 data across interactions. Build per-user 'what works' profile. Use profile to adjust all recommendation engines. | 5.4 (learning loop) | Platform learns individual preferences | Not Started
8.3 | Stage 8 | Phase Transition Detection | MEDIUM | Sara | Detect grief phase shifts (sustained mood improvement, task patterns, reduced crisis, self-reported changes). Adjust support mode defaults, tool families, companion behavior. 'Your journey is evolving' acknowledgment. | 1.5 (analytics), 5.4 (learning) | Platform adapts as grief evolves | Not Started
8.4 | Stage 8 | Task Automation Layer | HIGH | Sara | Phase 1: assist actions for documents (6), identity (8), employer (6) tasks. Phase 2: health (5), government (4), property (6). Phase 3: remaining. Add operation specs to 96 tasks. Expand assist widgets from 15 to 50+. | 3.1 (readiness) | Tasks have real automation | Not Started
8.5 | Stage 8 | Official Links Completion | MEDIUM | Sara | Add verified government/organization URLs to all 64 tasks missing them. Verify all URLs resolve. Mark US-specific with us_only flag. | None (independent) | All tasks have real resources | Not Started
8.6 | Stage 8 | Client-Side Tracking Migration | MEDIUM | Sara | Migrate ptg-tracking, outcome-tracking, dose-management from localStorage to Supabase. Persist across devices and sessions. Sync with server-side dose enforcement from Stage 1. | 1.1 (RLS), 1.6 (server-side doses) | Data persists across devices | Not Started

## Gate Checklist
STAGE GATES — Definition of Done
Stage | Gate # | Requirement | Status | Notes
Stage 1 | 1.G1 | Zero SECURITY DEFINER bypass except set_active_journey and get_invite_by_token | Pending
Stage 1 | 1.G2 | pgTAP test suite passes: no cross-user data access | Pending
Stage 1 | 1.G3 | debug_list_policies() removed from production | Pending
Stage 1 | 1.G4 | get_user_journeys() has auth.uid() validation restored | Pending
Stage 1 | 1.G5 | vault_supporters policies use denormalized column, not JWT claims | Pending
Stage 1 | 1.G6 | Crisis mode suppresses all non-safety content across all surfaces | Pending
Stage 1 | 1.G7 | Companion AI edge function receives support_mode and safety_flags | Pending
Stage 1 | 1.G8 | Crisis events logged to database | Pending
Stage 1 | 1.G9 | Core flows keyboard-navigable (sign-in, profiling, dashboard, task detail, vault PIN) | Pending
Stage 1 | 1.G10 | aria-live regions for all error/success messages | Pending
Stage 1 | 1.G11 | Vault PIN entry screen-reader-functional | Pending
Stage 1 | 1.G12 | All form inputs have aria-label or associated label | Pending
Stage 1 | 1.G13 | textFaint passes WCAG AA contrast | Pending
Stage 1 | 1.G14 | ToS and Privacy Policy links functional | Pending
Stage 1 | 1.G15 | getProgressEncouragement() returns real content | Pending
Stage 1 | 1.G16 | Analytics baseline live: onboarding funnel + feature engagement + crisis events | Pending
Stage 1 | 1.G17 | Dose limits enforced server-side | Pending
Stage 2 | 2.G1 | useCanonicalUserState() consumed by all major surfaces | Pending
Stage 2 | 2.G2 | ProfileSignalRegistry exists with all 68 questions mapped | Pending
Stage 2 | 2.G3 | hasSignal() prevents duplicate questions across T1/T2/T3 | Pending
Stage 2 | 2.G4 | Every answer propagates to all registered consumers within session | Pending
Stage 2 | 2.G5 | ClinicalRoute derived and consumed by LightKeeper, Marketplace, Today, Inner Light | Pending
Stage 2 | 2.G6 | ComprehensiveIntake removed or deprecated | Pending
Stage 2 | 2.G7 | TodayPayload contract defined and Today reads from it | Pending
Stage 3 | 3.G1 | Every task has computed TaskReadiness state | Pending
Stage 3 | 3.G2 | Task detail shows ONE missing thing and how to unblock | Pending
Stage 3 | 3.G3 | Vault navigable from task detail when documents required | Pending
Stage 3 | 3.G4 | Document upload updates task readiness in real time | Pending
Stage 3 | 3.G5 | Vault empty states warm and context-aware | Pending
Stage 3 | 3.G6 | Adaptive task count fully implemented with mode-appropriate language | Pending
Stage 3 | 3.G7 | Authority context visible on tasks that require it | Pending
Stage 4 | 4.G1 | Today moment interpretation consumes dominant suffering, practical burden, support environment, loneliness | Pending
Stage 4 | 4.G2 | Today section scoring accounts for task readiness and clinical route | Pending
Stage 4 | 4.G3 | At least one 'why this recommendation' explanation visible per session | Pending
Stage 4 | 4.G4 | LightKeeper first message warm and specific (uses profile data) | Pending
Stage 4 | 4.G5 | LightKeeper 'No messages yet' cold state eliminated | Pending
Stage 4 | 4.G6 | Companion AI receives full platform context | Pending
Stage 4 | 4.G7 | buildDynamicSystemPrompt() includes support mode, grief wave, tone, boundaries | Pending
Stage 4 | 4.G8 | First round of user research completed with findings documented | Pending
Stage 5 | 5.G1 | LightKeeperSupportProfile schema implemented with Supabase + RLS | Pending
Stage 5 | 5.G2 | Phase 1 (10 Qs) generates profile feeding LightKeeper, Today, Inner Light, escalation | Pending
Stage 5 | 5.G3 | Phase 1 respects signal dedup — never re-asks T1 data | Pending
Stage 5 | 5.G4 | Safety routing: crisis/professional signals stop matching, route to resources | Pending
Stage 5 | 5.G5 | 'Your support fit' summary displayed after Phase 1 | Pending
Stage 5 | 5.G6 | Phases 2-3 available progressively, not front-loaded | Pending
Stage 5 | 5.G7 | Phase 4 learning loop adjusts companion and triggers escalation | Pending
Stage 5 | 5.G8 | LightKeeper memory persists across conversations | Pending
Stage 5 | 5.G9 | Companion references prior conversations and shared facts | Pending
Stage 5 | 5.G10 | Matching engine outputs CompanionBehaviorProfile for system prompt | Pending
Stage 5 | 5.G11 | Escalation triggers defined and connected to Find Care | Pending
Stage 6 | 6.G1 | Inner Light tool selection considers depth readiness, dominant suffering, boundaries | Pending
Stage 6 | 6.G2 | Inner Light outcomes feed back to support profile | Pending
Stage 6 | 6.G3 | LightKeeper references Inner Light outcomes in conversation | Pending
Stage 6 | 6.G4 | Guide recommendations include active task categories | Pending
Stage 6 | 6.G5 | Task detail shows related guides; guide detail shows related tasks | Pending
Stage 6 | 6.G6 | Marketplace consumes clinical route and provider need likelihood | Pending
Stage 6 | 6.G7 | Today shows return narrative with continuity | Pending
Stage 6 | 6.G8 | All questions across T1/T2/T3/T4 have rationale text | Pending
Stage 6 | 6.G9 | T1/T2/T3 improvements implemented | Pending
Stage 6 | 6.G10 | Guide and Marketplace cold empty states eliminated | Pending
Stage 7 | 7.G1 | Supporters can see and help with delegated tasks | Pending
Stage 7 | 7.G2 | Provider routing considers clinical route and grief specialization | Pending
Stage 7 | 7.G3 | Hard-date awareness active across Today, LightKeeper, Inner Light | Pending
Stage 7 | 7.G4 | Document readiness visible at dashboard level | Pending
Stage 7 | 7.G5 | Warm professional handoff available with user consent | Pending
Stage 8 | 8.G1 | Route effectiveness tracked for all major recommendation types | Pending
Stage 8 | 8.G2 | What-helped / what-overwhelmed memory influences recommendations | Pending
Stage 8 | 8.G3 | Phase transition detection triggers appropriate adjustments | Pending
Stage 8 | 8.G4 | All 146 tasks have official links | Pending
Stage 8 | 8.G5 | Assist actions added to at least 50% of tasks (73+) | Pending
Stage 8 | 8.G6 | Client-side tracking synced to backend | Pending

## Cross-Cutting
CROSS-CUTTING ITEMS
Item | Starts | Finishes | Reason
Analytics instrumentation | Stage 1 | Ongoing | Must measure from the start
User research | Stage 4 | Ongoing | Continuous validation
LightKeeper memory design | Stage 4 (design) | Stage 5 (ship) | Long lead time for schema design
Official links | Any time | Stage 8 | Independent, no dependencies
Accessibility improvements | Stage 1 (critical) | Stage 6 (comprehensive) | Incremental improvement

## Not Building
WHAT WE ARE NOT BUILDING
The next leap is not more breadth. It is more coherence.
Item | Why Not
Workflow engine | Care Plan stays calm and simple on surface. No Gantt charts, no project management UI.
Social network | Peer matching is support-formulated, not social. No profiles, no browsing, no feeds.
Chatbot | LightKeeper is relational support with memory and clinical awareness, not generic AI chat.
Therapy replacement | Routes to professional care when insufficient. Never claims to provide therapy.
Data collection platform | Every question earns its place by improving the user's experience.
More LightKeeper personas | Not before continuity and memory work.
More Inner Light tools | Not before routing improves.
Sophisticated peer/social matching | Not before moderation and safety are ready.
Broad Marketplace polish | Not before clinical triage drives it.
Large Guides expansion | Not before adaptive surfacing improves.
Advanced ML optimization | Not before measurement is in place.
Broad visual redesigns | Not without stronger orchestration underneath.

## Production Ready
PLATFORM PRODUCTION-READY DEFINITION
# | Requirement | Status
1 | RLS test suite green, no bypass functions, permission model documented | Pending
2 | Crisis mode verified across all surfaces | Pending
3 | WCAG 2.1 AA ≥ 80% | Pending
4 | Analytics live with funnel + retention + feature engagement + crisis events | Pending
5 | No user asked the same question twice | Pending
6 | Companion AI receives full platform context | Pending
7 | LightKeeper memory persists across sessions | Pending
8 | Support formulation Phase 1 generates profile feeding whole platform | Pending
9 | Task readiness visible (ready / blocked / waiting) | Pending
10 | Vault linked to tasks | Pending
11 | At least 5 user testing sessions completed with findings incorporated | Pending
12 | All 146 tasks have official links | Pending
13 | Escalation routing works for crisis and professional-care needs | Pending
14 | Today feels like an orchestrator, not a dashboard | Pending
15 | The platform feels like one mind, not a collection of modules | Pending

## Governing Rules
GOVERNING RULES & PRIORITY ORDER
Rule | Description
Rule 1 | Every item answers: Does this make LightPath safer, more coherent, more emotionally intelligent, or more operationally useful for a grieving person at 2am?
Rule 2 | Priority order: 1) Trust and safety 2) Foundational shared systems 3) Visible intelligence 4) Operational usefulness 5) Continuity and ecosystem coordination 6) Learning and scale
Rule 3 | Every foundational block must unlock at least one felt user improvement. No invisible infrastructure marathons.
Rule 4 | Never run more than two major workstreams at once. Best pairing: one foundational/trust workstream + one visible intelligence/product-lift workstream.
Rule 5 | The next leap is not more breadth. It is more coherence.
MANAGEMENT RULE
For a small team or team of one: Never run more than two major workstreams at once. Best pairing: one foundational/trust workstream + one visible intelligence/product-lift workstream. That gives you: discipline, visible progress, less drift, less exhaustion.
FINAL VERDICT
This roadmap builds trust first, then intelligence, then experience, then learning. Every stage has a clear gate and a clear felt improvement. The single most important principle: a grieving person should never encounter a part of this platform that feels disconnected from what they already told it. That is the definition of coherence, and it is what this roadmap builds toward, stage by stage.